# Weekly Team Meeting Checklist

Purpose: This checklist is designed to keep weekly team meetings focused, efficient, and aligned with project goals. It ensures consistent progress tracking, clear ownership, and early identification of risks across product, UX, and research workstreams.

## 1. Pre-Meeting Preparation (Before the Meeting)

Each team member should complete the following before the meeting:

- Review notes and action items from the previous week

- Update any deliverables or documents owned by you

- Add agenda items or blockers to the shared meeting doc

- Flag any dependencies that may affect other team members

## 2. Meeting Kickoff (5 minutes)

- Confirm meeting agenda

- Identify facilitator and note-taker (rotate weekly if possible)

- Restate the current milestone or short-term goal

Checklist:

- ☐ Agenda confirmed

- ☐ Roles assigned

- ☐ Milestone restated

## 3. Individual Updates (20–25 minutes total)

Each team member gives a concise update (3–5 minutes each).

### For Each Team Member

- What did you complete since the last meeting?

- What are you currently working on?

- What are your next deliverables before the next meeting?

- Are there any blockers or dependencies?

Checklist (repeat per person):

- ☐ Completed tasks reviewed

- ☐ Current work summarized

- ☐ Next deliverables defined

- ☐ Blockers identified

## 4. Cross-Functional Alignment (10–15 minutes)

Use this section to ensure workstreams remain aligned.

### Product & Scope Alignment

- Are current tasks still aligned with the pilot scope?

- Has scope expanded unintentionally?

- Do any features require reprioritization?

Checklist:

- ☐ Scope still aligned

- ☐ No unapproved scope creep

- ☐ Priorities confirmed

### UX & Content Alignment

- Do UX designs match learning objectives?

- Are scenarios age-appropriate and realistic?

- Is the tone consistent across gameplay and narrative?

Checklist:

- ☐ UX and content aligned

- ☐ Age-appropriateness confirmed

- ☐ Feedback loops clear

## 5. Privacy, Ethics & Compliance Check (5 minutes)

This section ensures the project continues to model best privacy practices.

- Does any new feature introduce data collection?

- Are all features still COPPA-compliant?

- Are privacy explanations clear to both children and parents?

Checklist:

- ☐ No unnecessary data collection introduced

- ☐ COPPA compliance maintained

- ☐ Privacy-by-design principles upheld

## 6. Risks & Blockers Review (5–10 minutes)

Discuss anything that could delay progress or affect quality.

- Technical constraints

- Design limitations

- Research gaps

- Time or workload concerns

Checklist:

- ☐ Risks identified

- ☐ Mitigation steps discussed

- ☐ Owner assigned to each risk

## 7. Decisions Made This Week (5 minutes)

Document any decisions clearly to avoid re-litigation later.

- What was decided?

- Why was it decided?

- Does it affect scope, timeline, or design?

Checklist:

- ☐ Decisions documented

- ☐ Rationale captured

- ☐ Impacts understood

## 8. Action Items & Ownership (5 minutes)

Clearly assign next steps before ending the meeting.

For each action item:

- Owner

- Description

- Deadline

Checklist:

- ☐ Action items listed

- ☐ Owners assigned

- ☐ Deadlines confirmed

## 9. Prep for External Check-Ins (If Applicable)

If an advisor or stakeholder meeting is upcoming:

- What progress should be shown?

- What questions need answers?

- What materials must be ready?

Checklist:

- ☐ Materials identified

- ☐ Talking points outlined

- ☐ Owners assigned

## 10. Post-Meeting Wrap-Up (After the Meeting)

Within 24 hours:

- Upload notes to shared repository

- Update project timeline or task board

- Share summary with absent members

Checklist:

- ☐ Notes shared

- ☐ Tasks updated

- ☐ Follow-ups sent

## Optional: Weekly Health Check

- Team workload manageable?

- Communication clear?

- Timeline still realistic?

Checklist:

- ☐ Workload balanced

- ☐ Communication effective

- ☐ Timeline feasible

Outcome: If every box is checked weekly, the project should stay on track, aligned, and ready for advisor or ITS review at any point.