Privacy Video Game — Pilot Milestone Timeline

February 25, 2026  →  May 1, 2026    |  Product Lead: Eric Nielsen  |  Status: Active

|  | Phase 1: Foundation |  | Phase 2: Design & Content |  | Phase 3: Build |  | Phase 4: Testing |  | Phase 5: Polish & Handoff |  | Milestone / Deadline |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Week | Dates | Milestone | Owner(s) | Key Deliverables |
| --- | --- | --- | --- | --- |
| PHASE 1 — Foundation & Alignment (Weeks 1–2) |  |  |  |  |
| Wk 1 | Feb 25 – Mar 1 | Kickoff & Repo Setup | Eric | • GitHub repo organized & populated • mockup + docs committed • team roles confirmed |
| Wk 2 | Mar 2 – Mar 8 | Milestone Planning & Compliance Review | Eric + All | • This timeline distributed to team • COPPA compliance checklist drafted • weekly meeting cadence locked |
| PHASE 2 — UX Design & Content Development (Weeks 3–4) |  |  |  |  |
| Wk 3 | Mar 9 – Mar 15 | UX Wireframes (Scenario 1) | Sarafina | • Low-to-mid fidelity wireframes for Scenario 1 • child & parent user flows • onboarding draft |
| Wk 4 | Mar 16 – Mar 22 | Scenario Scripts & NPC Dialogue | Grace + Sarafina | • Full Scenario 1 script • Ted's dialogue library • in-game explanations written • learning objectives mapped |
| ⚠️ Spring Break Buffer — Mar 23–29 (reduced velocity expected) |  |  |  |  |
| Wk 5 | Mar 23 – Mar 29 | Buffer / Async Catch-Up | All | • Address backlog items • review research bibliography • prep for development sprint |
| PHASE 3 — Development Sprint (Weeks 6–7) |  |  |  |  |
| Wk 6 | Mar 30 – Apr 5 | Scenario 1 Full Build | Eric + Sarafina | • Scenario 1 fully implemented from mockup • UX integrated with scripts • Ted dialogue wired in |
| Wk 7 | Apr 6 – Apr 12 | Scenario 2 Build (Stretch) + Internal QA | Eric + Sarafina | • Scenario 2 (App Permissions) if on track • internal QA pass on Scenario 1 • bug fixes • accessibility review |
| PHASE 4 — Usability Testing & Iteration (Weeks 8–9) |  |  |  |  |
| Wk 8 | Apr 13 – Apr 19 | Usability Testing | Grace + Sarafina | • Testing sessions with children ages 9–13 • observation notes • ITS / advisor demo session |
| Wk 9 | Apr 20 – Apr 26 | Iteration & Findings Synthesis | All | • UX fixes from testing • evaluation criteria results • updated learning objectives if needed |
| PHASE 5 — Polish, Documentation & Handoff (Week 10) |  |  |  |  |
| Wk 10 | Apr 27 – May 1 | Final Handoff & Stakeholder Review | Eric | • Final handoff doc for ITS / interns • stakeholder-facing summary • repo finalized • pilot declared complete |
| 🏁 PILOT COMPLETE — May 1, 2026 |  |  |  |  |

# Planned Advisor & Stakeholder Check-Ins

| Date | Meeting | Goal | Materials Needed |
| --- | --- | --- | --- |
| ~Mar 8 | Sol (3-wk check-in) | Validate scope & timeline; confirm priorities | This timeline, mockup link, pilot scope doc |
| ~Mar 22 | ITS (initial intro) | Orient ITS to project; surface hosting / tech questions | Project overview, technical notes, mockup |
| ~Apr 5 | Advisor / Privacy@Michigan | Mid-build feedback on design and learning objectives | Wireframes, scenario scripts, partial build |
| ~Apr 19 | Sol (3-wk check-in) | Review usability testing findings; adjust if needed | Testing notes, updated build |
| May 1 | Final Stakeholder Presentation | Demonstrate pilot; hand off to ITS; present findings | Final build, handoff doc, evaluation summary |

Privapals Pilot — Milestone Timeline v1  |  February 2026  |  Subject to revision at weekly team meetings